## sales strategy
Sales Strategy
| Strategic Goal | Strategic Initiative | Strategic meassur. Final goal | Hlm | E/A | Hbg | Ofm | Lby | vxö | Hld | Completion date | Comments
Business system | All salesmen use Caesar | JOA educate Olofström office | Min. 10 salesactivities/saleaman in Ceasar | [7 empty] | 2005-04-22 | OK competetors added and Ofm-template to be updated
| BBT Meting (IK) developes | Tore Chairman, calls to 1.st meting incl. A suggested agenda | Each salesman presents the most important quotes,activities, contacts, info, etc | [7 empty] | Start 2005-05-02 | Tore to call to meting W17
| Common CRM-system in Epsilon | Patric Englund responsible | More efficient sales process | [7 empty] | Ongoing | OK + Dennis / Koncernen
Marketing mat./Shows | New Broschyr | On Hold | Come up with suggestion | [7 empty] | On Hold | On Hold
| New PowerPoint Presentation mat. | Patric O responsible | Come up with suggestion | [7 empty] | 2005-06-30 | Inventory started by P.o. Kalle Norbo to check status
| Common CV template to be used | Tore send out template | All CV's | [7 empty] | genomfört 2005-04-07 | Not done Offices at different timeschedule
| New reference project template | Tore send out template | [8 empty] | genomfört 2005-04-08 | OK
| New reference projects | PC Start up/delegate | 3 per department to be added | [7 empty] | 2005-06-30 | Not done Offices at different timeschedule
| Workshop | On Hold | Min 1 new customer | [7 empty] | On Hold | On Hold
Business judgement | Customer analysis | IA resp. Fredrik to come up with 1.st draft of material and templates. Coordinate with Tores new BBt. SA helps with excel | To be done min. on the 10 largest customer (info input in Ceasar) | [7 empty] | 2005-09-30 | Cearsar to be used correctly from the start. Anybody can select and we work actively scanning the list every week. If nessecary more documents added+FINAL DATES MUST BE USED IN CEASAR
| Business analysis |  | To be applied on min. 20 businessdeals, to identify poor profit deals. | [7 empty] | 2005-05-31
| Prognosis Quotation- hit-rate results |  | To be able to make smarter/faster sales decitions in the future | [7 empty] | 2005-05-31
New Markets/Offers | Tackel new market, Government purchase (Powerplants, Defense, etc. | Patric Englund to start emmidiatly to gain knowledge about this area | 1 new customer | [7 empty] | 2005-12-31 | Yearly results, taxissues to be collected so it can be sent in as a package at rfq. Free version of system to be analysed. 1 quote allready sent in
| Competition analysis | On Hold | To be done on the 3 biggest competitors | [7 empty] | 2005-12-31 | On Hold
| Inventory of special competence IK | Arrange together with CV update and development talks | To be used in special marketing in the future | [7 empty] | 2005-12-31 | Not ready. Offices at diff. Timeschedules.Issue added to Qstd to be used at Pers. Dev. Talks. Results to be handled. Special competence, i.e technical, language, etc
| Internal competence and reference transfer | JPK to find suitable objects | 1 new customer for turnkey project outside automotive | [7 empty] | 2005-12-31 | Brought up on internal sales meting IL and to be reported 1/month
|  | DO IT | [8 empty] | Done
|  | PRIORITY 1 | [8 empty] | Started
|  | ON HOLD | [8 empty] | Not Started
On Hold